# Proposal: Clinic scheduling and records upgrade

Prepared for Northfield Clinic by Jordan Lee, Acme Co.

## Summary

Northfield Clinic has grown to three doctors and eleven staff, but patients still fill in paper forms and book by phone. This proposal sets out a four-month project to move intake forms online, connect booking to your scheduling system, and make ten years of scanned records searchable.

## What we will deliver

- Secure online intake forms that patients complete before they arrive

- Online booking connected to your existing scheduling system

- A searchable archive of scanned records

- Training for reception and clinical staff, and a month of support

## Timeline

| Phase | Weeks | Outcome |
| --- | --- | --- |
| Discover | 1 to 2 | Current process mapped with the reception team |
| Forms | 3 to 6 | Online forms live for new patients |
| Booking | 7 to 11 | Booking connected and tested |
| Archive and training | 12 to 16 | Records searchable, staff trained |

## Investment

| Milestone | Amount |
| --- | --- |
| Signed agreement | $12,000 |
| Online forms live | $16,000 |
| Booking connected | $14,000 |
| Archive and training | $10,000 |
| Total | $52,000 |

## Next steps

- Dana Whitfield reviews this proposal with the partners.

- Acme sends the service agreement for signature.

- Kick-off at the clinic on 6 October.